

**Code of practice for the**

March 2023


**co-ordination of street and road**

**works**

Department for Transport Great Minster House

33 Horseferry Road

London SW1P 4DR



© Crown copyright 2023

This publication is licensed under the terms of the Open Government Licence v3.0 except where otherwise stated. To view this licence, visit <https://www.nationalarchives.gov.uk/doc/open-government-licence/version/3/> or contact, The National Archives at [www.nationalarchives.gov.uk/contact-us.](http://www.nationalarchives.gov.uk/contact-us.)

Where we have identified any third-party copyright information you will need to obtain permission from the copyright holders concerned.

This publication is also available on our website at [www.gov.uk/government/organisations/department-for-transport](http://www.gov.uk/government/organisations/department-for-transport)

Any enquiries regarding this publication should be sent to us at [www.gov.uk/government/organisations/department-for-transport](http://www.gov.uk/government/organisations/department-for-transport)

Contents

Executive summary 6

Chapter 1 - Introduction 8

1.1 Introduction 8

1.2 Legislative framework 9

1.3 Other statutory obligations 10

Chapter 2 – Co-ordination and collaboration 12

2.1 Introduction 12

2.2 Information 12

2.3 Analysis and assessment considerations 15

2.4 Co-operation 16

2.5 Collaborative working 16

Chapter 3 - The national street gazetteer 22

3.1 Introduction 22

3.2 The local and national street gazetteers 22

3.3 Additional street data 22

3.4 Maintaining and updating the LSG and ASD 24

Chapter 4 - Register of works in a street 28

4.1 Introduction 28

4.2 Public access to information contained in street manager 29

4.3 Entering information on the register 29

4.4 Requirements for Street Manager 29

Chapter 5 - Streets subject to special controls 31

5.1 Introduction 31

5.2 Protected streets 32

5.3 Streets with special engineering difficulties (SED) 33

5.4 Traffic-sensitive streets 36

5.5 Procedure for making designations 38

5.6 Review procedure 40

Chapter 6 - Restrictions 42

6.1 Introduction 42

6.2 Substantial works – definitions 43

6.3 Creating a restriction 44

6.4 Duration of restrictions 48

6.5 Works during a restriction 49

6.6 Policy guidance 51

6.7 Dispute resolution 52

Chapter 7 - Works' classification 53

7.1 Introduction 53

7.2 Legislative background 53

7.3 Works requiring a permit 56

7.4 Categorisation of works 59

Chapter 8 - General principles 62

8.1 Introduction 62

8.2 Common rules 63

8.3 Notification types 64

8.4 Process in the event of Street Manager being unavailable 66

Chapter 9 - Guidance on when a validity window applies 67

9.1 Introduction 67

9.2 Explaining the validity window 67

9.3 Guidance on the start date under NCT01a – planned works 68

9.4 Guidance on using the validity window under NCT01b – planned works 68

Chapter 10 - Charging schemes 70

10.1 Introduction 70

10.2 Section 74A – charge determined by reference to duration of works 70

10.3 Section 74 – charge for occupation of the highway where works

unreasonably prolonged 70

10.4 Exempt works 71

10.5 Prescribed period 72

10.6 Reasonable period 72

10.7 Duration of works 73

10.8 Notification timescales for actual start and works closed 74

10.9 Formal warning 76

10.10 Charging regime 76

10.11 Mitigated charges 79

10.12 Remedial works and subsequent phases 80

10.13 Charging process 80

Chapter 11 - Fixed penalty notices 82

11.1 Introduction 82

11.2 Fixed penalty offences 83

11.3 Penalty charges and time periods 85

11.4 Guidance for authorities 87

11.5 Guidance for promoters 88

11.6 Representations 88

11.7 General guidance 89

Chapter 12 - Related matters 90

12.1 Introduction 90

12.2 Road closures and traffic restrictions 90

12.3 Duty to maintain apparatus 94

12.4 Working near to rail tracks and tramways 97

12.5 Vehicle parking at street and road works 97

12.6 Traffic signals 98

12.7 Storage of materials and other equipment 99

12.8 Apparatus belonging to others 99

Chapter 13 - Dispute resolution 100

13.1 Introduction 100

13.2 Dispute review 100

13.3 Adjudication 101

13.4 Arbitration 101

Appendices 102

Appendix A: Glossary 103

Appendix B: HAUC (England) permit guidance 109

Appendix C: Works at or near level crossings 110

Appendix D: Forward planning and co-ordination 111

Appendix E: Collaboration framework 112

Appendix F: Current list of special designations 114